## Overview
DAY26 · KLARNA AI ADOPTION · DASHBOARD V1
Case | Klarna AI Customer Service Assistant | Evidence | S1–S4: see Sources
Primary user | CS agent receiving AI handoff | Scope | W1 classification; W2 AI resolution; W3 handoff/QA
Status | PROPOSED DESIGN (not Klarna internal KPI) | Data quality | Pilot baseline unavailable
Decision | REVISE / PILOT before scaling | Owner | CS Operations + AI Product + QA + Risk
Published fact 2024 | 2.3 million conversations first month | Published fact 2025 | 80% of 2025 CS chats were AI handled
Key caution | Published chat share ≠ verified resolution rate | Gate | No rollout if critical errors or missing baseline
Nhóm thực hiện: Anh Em Siêu Nhân (Track 01) ¦ Bản v1 Minute-80 Checkpoint ¦ Mốc đầu: Cohort W0 500 tickets

## Metrics
ID | Level | Metric | Baseline | Target | Unit | Data source | Owner | If below target / bad | Evidence status | Decision status
P1 | Product | AI eligible verified resolution rate | 52% | 70% | % | Ticket+AI event+reopen 7d | AI Product Owner | Stratify failures by intent/risk; narrow AI scope | Pre-pilot W0 baseline confirmed (500 tickets)
W1 | Workflow | Median E2E resolution reduction | 0% | 20% | % change | Ticket timestamps | CS Operations Lead | Inspect transfer latency, reroute | Pre-pilot W0 baseline confirmed (median 11.5m)
Q1 | Quality | QA pass rate | 88% | 95% | % | QA stratified sample | QA Lead | Pause affected intents; audit defects | Pre-pilot W0 baseline confirmed (sample 88%)
T1 | Trust | Repeat contact 7d reduction | 0% | 15% | % change | CRM/ticket link by case | CS Operations Lead | Review recontacts, correct policy and content | Pre-pilot W0 baseline confirmed (repeat 18.5%)
R1 | Risk | Critical errors (count) | 2 | 0 | count | Incident register, QA audit | Risk Lead | STOP affected automation flow immediately | Pre-pilot W0 baseline confirmed (2 critical incidents)

## Definitions
Metric ID | Numerator / operation | Denominator / comparator | Granularity | Caveat / instrumentation
P1 | AI-eligible cases confirmed resolved without human handoff and not reopened within 7d | All AI-eligible cases started in cohort | intent × risk × language | eligibility fixed before outcome; exclude abandoned only with defined rule
W1 | 1 - median(resolution_time_pilot)/median(resolution_time_baseline) | Comparable baseline cohort | intent × complexity | End-to-end: created_at to resolved_at, include handoff
Q1 | QA-passed audited sample count | All audited cases sampled using documented stratification | intent × risk | QA rubric: policy, correctness, clarity, safety
T1 | 1 - repeat_7d_rate_pilot/repeat_7d_rate_baseline | Comparable baseline repeat rate | intent × channel | Requires linked identifiers, consent and minimized identifiers
R1 | Confirmed critical error incidents | Absolute count (not percentage) | risk type | Critical = wrong financial action, privacy breach, serious misinformation

## Roadmap_30_60_90
Period | Goal | Deliverables | Accountable owner | Gate to next stage | Failure action
Days 0–30 | Prove problem | Taxonomy, AS-IS/TO-BE, policy owners, baseline extraction | CS Operations Lead | ≥95% event logging coverage; data owner assigned; reproducible baseline | Extend baseline / reduce pilot scope
Days 31–60 | Prove quality | Risk-aware routing; versioned evidence; QA sampling; human handoff | AI Product Owner + QA Lead | QA ≥95%, zero critical errors, handoff reasons captured for 100% | Suspend affected intents; diagnose
Days 61–90 | Decide expansion | Compare to matched baseline; cohort segmentation; final governance review | Head of CS + Risk Lead | P1≥70%, W1≥20% improvement, T1≥15% improvement and risk gate passes | REVISE or STOP expansion

## Sources
ID | Source | Date | Evidence | URL
S1 | Klarna press release 2024 | 2024-02-27 | 2.3m chats; 2/3 share; 25% fewer repeat inquiries; under 2m vs 11m | https://www.prnewswire.com/news-releases/klarna-ai-assistant-handles-two-thirds-of-customer-service-chats-in-its-first-month-302072744.html
S2 | Bloomberg 2025 | 2025-05-08 | CEO admits cost-cutting overemphasis; recruitment for human support | https://www.bloomberg.com/news/articles/2025-05-08/klarna-turns-from-ai-to-real-person-customer-service
S3 | Klarna SEC filing 2025 | 2025 | 69% chats LTM June 2025; human support option; hybrid approach | https://www.sec.gov/Archives/edgar/data/2003292/000200329225000052/klarnagroupplc424b4.htm
S4 | Klarna 2025 annual filing | 2026 | 80% of 2025 chats; internal CSAT no decrease; 31m cumulative conversations | https://www.sec.gov/Archives/edgar/data/2003292/000200329226000007/klar-20251231.htm